## Project Planner
Project Planner |  |  |  |  | Start Date: 28th january
Select a period to highlight to the right. A legend describing the chart follows. |  |  |  |  | Period Highlight: | 7 |  |  | Plan Duration | [5 empty] | Actual Duration |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
TASKS | PLAN START | DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Project planning | 1 | 33 | 1 | 6 | 0%
Group sign up | 1 | 1 | 1 | 1 | 100%
Vision of project | 1 | 1 | 1 | 1 | 70%
Code of conduct | 1 | 1 | 1 | 1 | 0%
Ethical Approval | 1 | 1 | 1 | 1 | 0%
Group meetings | 1 | 1 | 1 | 1 | 0%
Terms of reference | 8 | 2 | 0 | 0 | 0%
Scope of the project (team)
Team system requirements
Team requirements spec for common elements | 8 | 2 | 0 | 0 | 0%
Legal, social, ethical and professional document | 8 | 2 | 0 | 0 | 0%
Scope of the project (subcomponent) | 10 | 1 | 0 | 0 | 0%
requirements analysis for subcomponent | 10 | 1 | 0 | 0 | 0%
Requirements spec for individual elements
Project tasks, deliverables and costing | 11 | 6 | 0 | 0 | 0%
agreed deliverables
resource list | 17 | 2 | 0 | 0 | 0%
testing procedures/stratergy for project | 17 | 1 | 0 | 0 | 0%
risk analysis | 17 | 1 | 0 | 0 | 0%
project plan | 18 | 1 | 0 | 0 | 0%
project costing
Project devlopment | 19 | 1 | 0 | 0 | 0%
devolping subsystem1 | 20 | 3 | 0 | 0 | 0%
devolping subsystem 2 | 20 | 3 | 0 | 0 | 0%
devolping subsystem 3
devolping subsystem 4 | 23 | 3 | 0 | 0 | 0%
devolping subsystem 5 | 23 | 2 | 0 | 0 | 0%
Weekly reviews of code | 24 | 2 | 0 | 0 | 0%
Weekly grouping of subsystem code for website
Testing indivdual subsytem
Testing overall website
Presenting the demo
Testing every aspect of website
Practice run through of demo
Personal Evalutaion