## Project Planner
Project Planner |  |  |  |  | Start Date: 1st October (Period 1)
Select a period to highlight to the right. A legend describing the chart follows. |  |  |  |  | Period Highlight: | 7 |  |  | Plan Duration | [5 empty] | Actual Duration |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
TASKS | PLAN START | DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Project Management | 1 | 33 | 1 | 6 | 0%
Project Initiation Document | 1 | 3 | 2 | 2 | 100%
Revised Terms of Reference (with ethics form) | 4 | 4 | 4 | 4 | 70%
Submit Analysis Chapters | 8 | 2 | 0 | 0 | 0%
Supervisional Meetings | 1 | 33 | 1 | 7 | 0%
Research | 6 | 2 | 0 | 0 | 0%
Compile findings for literature review | 6 | 2 | 0 | 0 | 0%
Compile findings for Technical review | 6 | 2 | 0 | 0 | 0%
Learning/Enhacing Skills | 8 | 2 | 0 | 0 | 0%
Learn fundementals of Swift | 8 | 2 | 0 | 0 | 0%
Learn functionality of xCode | 8 | 2 | 0 | 0 | 0%
Designing Protype | 10 | 1 | 0 | 0 | 0%
Developing UI designs | 10 | 1 | 0 | 0 | 0%
Developing Protype | 11 | 6 | 0 | 0 | 0%
Develop the application | 11 | 6 | 0 | 0 | 0%
Testing | 17 | 2 | 0 | 0 | 0%
Usability testing | 17 | 1 | 0 | 0 | 0%
Functionality testing | 17 | 1 | 0 | 0 | 0%
Pilot test | 18 | 1 | 0 | 0 | 0%
Experimental Work | 19 | 4 | 0 | 0 | 0%
Prepare for experiment | 19 | 1 | 0 | 0 | 0%
Conduct experiment | 20 | 3 | 0 | 0 | 0%
Collect all data (Surveys) | 20 | 3 | 0 | 0 | 0%
Analysing Results | 23 | 3 | 0 | 0 | 0%
Review data from experiment | 23 | 2 | 0 | 0 | 0%
Compose a evaluation of data | 24 | 2 | 0 | 0 | 0%
Project Report | 8 | 26 | 0 | 0 | 0%
Develop a report plan | 8 | 2 | 0 | 0 | 0%
Develop report | 10 | 21 | 0 | 0 | 0%
Review report | 31 | 2 | 0 | 0 | 0%