## Project Planner
Project Planner |  |  |  |  | Start Date: 28th january
Select a period to highlight to the right. A legend describing the chart follows. |  |  |  |  | Period Highlight: | 4 |  |  | Plan Duration | [5 empty] | Actual Duration |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
TASKS | PLAN START | DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Project Management
Weekly meetings with group | 1 | 15 | 1 | 4 | 0%
Project planning
Vision of project | 1 | 2 | 1 | 2 | 100%
Code of conduct | 1 | 2 | 1 | 2 | 100%
Ethical Approval | 2 | 4 | 2 | 0 | 50%
Terms of Reference
Scope of the project (team system spec) | 2 | 4 | 2 | 0 | 50%
Scope of the project (subcomponent) | 2 | 4 | 2 | 0 | 50%
Project tasks, deliverables and costing | 2 | 4 | 2 | 0 | 50%
Project devlopment
Devolpment of Subsystem 1 | 4 | 4 | 0 | 0 | 0%
Devolpment of Subsystem 2 | 4 | 4 | 0 | 0 | 0%
Devolpment of Subsystem 3 | 4 | 4 | 0 | 0 | 0%
Devolpment of Subsystem 4 | 4 | 4 | 0 | 0 | 0%
Devolpment of Subsystem 5 | 4 | 4 | 0 | 0 | 0%
Testing and intergration
Testing of subsytems, seperatly | 9 | 1 | 0 | 0 | 0%
Intergate subsystems together | 10 | 1 | 0 | 0 | 0%
whole system testing | 10 | 1 | 0 | 0 | 0%
Code quality check | 11 | 1 | 0 | 0 | 0%
Presenting the demo |  |  |  |  | 0%
Practice run through of demo | 11 | 1 | 0 | 0 | 0%
Present demo of software | 12 | 1 | 0 | 0 | 0%
Reflection |  |  |  |  | 0%
Completing the project evaluation | 12 | 15 | 0 | 0 | 0%